| # Date | # Item | # Action | # Entity Responsibility |
| --- | --- | --- | --- |
| March 2026 | CoC Registration Review Opened | Agency/Project Applicants review for accuracy Grant Inventory Worksheet (GIW) | CoC Lead, Planning, project applicants |
| March 2026 | CoC GIW Review | GIW reviewed for accuracy | CoC Lead, Planning, project applicants |
| 6/1 | FY 2026 NOFO released | Begin thorough review of NOFO | CoC Lead, Planning Agency |
| 6/24 | Executive Summaries | Send guidelines to renewal project applicants for executive summaries | CoC Lead/HUD Community Resources Staff |
| 6/24 | Public Notice Release | Notify public of release of FY 2026 NOFO, post on social media, lead agency website, community newsletter | Planning Agency, CoC Lead |
| 6/24 | Timeline Shared | Publicly Post Competition Timeline | Planning Agency |
| July 2026 | Review of Ranking Process | Meet with City HUD Community Resources Division | CoC Lead/HUD CRD Staff |
| July 2026 | Notify Perspective Ranking Committee Members | Send email to obtain interest and scheduling | HUD Community Resources Staff, CoC Board Chair |
| 7/24 | Project Application Executive Summaries | Executive Summaries due to City HUD Community Resources Division | Project applicants |
| 8/5 | CoC Application | Draft Copy of Application to CoC Lead/Planning for review | CoC Lead/Planning |
| August 2026 | Ranking Committee Meets | HUD Community Resources Division and Ranking Committee | HUD Community Resources Division/CoC Lead |
| 8/11 | CoC Lead | Notice of Project Acceptance/Rejection and Ranking sent to applicants | CoC Lead |
| 8/14 | Planning Agency/CoC Chair | Final Draft of Consolidated Application Due | CoC Lead |
| 8/14 | Final CoC Application | Submit completed application to City Manager for review | Planning Agency/CoC Chair |
| 8/25 | Final CoC Application | Submit Final CoC Competition application | Planning Agency/CoC Chair |

HUD CoC Submission Deadline – August 26, 2026