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Blue Ridge CoC FY 2026 CoC Competition Timeline
	Date
	Item
	Action
	Entity Responsibility

	March 2026
	CoC Registration Review Opened 
	Agency/Project Applicants review for accuracy
Grant Inventory Worksheet (GIW)
	CoC Lead, Planning, project applicants

	March 2026
	CoC GIW Review 
	GIW reviewed for accuracy
	CoC Lead, Planning, project applicants


	6/1
	FY 2026 NOFO released
	Begin thorough review of NOFO
	CoC Lead, Planning Agency

	6/24
	Executive Summaries
	Send guidelines to renewal project applicants for executive summaries
	CoC Lead/HUD Community Resources Staff

	6/24
	Public Notice Release
	Notify public of release of FY 2026 NOFO, post on social media, lead agency website, community newsletter
	Planning Agency, CoC Lead

	6/24
	Timeline Shared
	Publicly Post Competition Timeline
	Planning Agency

	July 2026
	Review of Ranking Process
	Meet with City HUD Community Resources Division
	CoC Lead/HUD CRD Staff

	July 2026
	Notify Perspective Ranking Committee Members
	Send email to obtain interest and scheduling
	HUD Community Resources Staff, CoC Board Chair

	7/24
	Project Application Executive Summaries
	Executive Summaries due to City HUD Community Resources Division 
	Project applicants

	8/5
	CoC Application
	Draft Copy of Application to CoC Lead/Planning for review
	CoC Lead/Planning

	August 2026
	Ranking Committee Meets
	HUD Community Resources Division and Ranking Committee
	HUD Community Resources Division/CoC Lead

	8/11
	CoC Lead
	Notice of Project Acceptance/Rejection and Ranking sent to applicants
	CoC Lead

	8/14
	Planning Agency/CoC Chair
	Final Draft of Consolidated Application Due
	CoC Lead

	8/14
	Final CoC Application
	Submit completed application to City Manager for review
	Planning Agency/CoC Chair

	8/25
	Final CoC Application
	Submit Final CoC Competition application
	Planning Agency/CoC Chair



	
HUD CoC Submission Deadline – August 26, 2026
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